## Trang_tính1
CAPSTONE 3 : REACT MOVIE
STT | Task Name | Start Build | Finish Build | %Build | Names Dev | Start Testing | Finish Testing | % Testing | Names Dev | Notes
| USER |  |  | 100% |  |  |  | 100% |  | Completed
I | HomePage
1 | Header | 2024-04-07 | 2024-04-07 |  | Nguyen Thi Be Ngoan | 2024-04-10 | 2024-04-11 |  | Nguyen Thi Be Ngoan
*2 | Banner | 2024-04-26 | 2024-04-28 |  | Nguyen Thi Be Ngoan | 2024-04-29 | 2024-04-30
3 | ListMovie | 2024-04-07 | 2024-04-08 |  | Nguyen Anh Truyen | 2024-04-10 | 2024-04-11
4 | LichChieuRap | 2024-04-07 | 2024-04-09 |  | Nguyen Thi Be Ngoan | 2024-04-11 | 2024-04-15
5 | Footer | 2024-04-27 | 2024-04-28 |  | Nguyen Thi Be Ngoan | 2024-04-29 | 2024-04-29
II | SignIn | 2024-04-07 | 2024-04-10 |  | Nguyen Thi Be Ngoan | 2024-04-10 | 2024-04-12 |  | Nguyen Thi Be Ngoan
III | DetailPage |  |  |  | Nguyen Thi Be Ngoan |  |  |  | Nguyen Thi Be Ngoan
1 | MovieDetail | 2024-04-08 | 2024-04-10 |  |  | 2024-04-12 | 2024-04-17
**2 | CumrapDetail | 2024-04-10 | 2024-04-15 |  |  | 2024-04-20 | 2024-04-22
IV | TicketBookingPage |  |  |  | Nguyen Thi Be Ngoan |  |  |  | Nguyen Thi Be Ngoan
1 | SeatSelector
** | SeatGrid | 2024-04-12 | 2024-04-17 |  |  | 2024-04-23 | 2024-04-26
| SeatNote | 2024-04-12 | 2024-04-17 |  |  | 2024-04-23 | 2024-04-26
**2 | TicketBookingCard | 2024-04-18 | 2024-04-25 |  |  | 2024-04-26 | 2024-04-29
| ADMIN |  |  | 100% | Nguyen Anh Truyen |  |  | 100% | Nguyen Anh Truyen | Completed
I | MovieManager | 2024-04-08 | 2024-04-15 |  |  | 2024-04-17 | 2024-04-19
II | AddMovie | 2024-04-08 | 2024-04-12 |  |  | 2024-04-16 | 2024-04-17
III** | EditMovie | 2024-04-13 | 2024-04-26 |  |  | 2024-04-27 | 2024-04-30
IV | ShowTime | 2024-04-15 | 2024-04-17 |  |  | 2024-04-26 | 2024-04-27
V | SignUp | 2024-04-12 | 2024-04-14 |  |  | 2024-04-15 | 2024-04-16
DEPLOY WEB VERCEL |  | Nguyen Thi Be Ngoan Nguyen Anh Truyen